## Sheet1
Task ID | PB Task | User Story | Tasks | Status | Allocation | Effort Remaining
[6 empty] | Estimated Effort (hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
3 | Remote Webpage Development | As a user, I want to be able to control Pepper remotely through the website without needing to physically interact with her. | Develop Pepper Controls - (link design template to peppers comand api) | Started | Abigail Smith | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
|  | As a developer i need to link the UI of the webpage to peppers controll comands. | Link Pepper Controls (have the webpages interact the created controls) | Started | Abigail Smith, Mykyra Kakaranza | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3
| Remote Website Design | As a developer, I want to be able to have templates i can follow when implementing HTML and css elements | Design mockups for remote webpages | Finished | Calla Aitken | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | As a user, I want to have webpages to look at and interact with | Create webpages | Started | Kate Leggott | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
|  | As a user, I want to be able to easily understand where i can find different functions to control Pepper with | Implement easy to navogate interfaces for different functions of pepper | Started | Kate Leggott | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| Interactive Tablet Design | As a user, I want the webpages to be simple to use and understand | UX Research | Finished | Stuart Lancaster | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
|  | As a developer, I want to plan out how the webpages should look so that I have a plan when coding | Design mockups for the tablet webpages | Finished | Calla Aitken | 4 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | As a developer, I need to produce functional webpages that people can interact with | Create tablet webpages | Started | Stuart Lancaster & Mykyta Kakaranza | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 3 | 0
|  | As a user, I want to be able to understand pepper clearly | Introduce speech-to-text function on pepper interface | Not started | Mykyta Kakaranza | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
9 | Controller Support | As a user, i want to control pepper using a gamepad (xbox controler) | learn HTML5 gamepad api | Finished | Stuart Philpot | 5 | 5 (5 Hrs Worked) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | As a developer, i need to learn the HTML5 gamepad api, peppers native api, and johns javascript api and put them all together | learn peppers native API (to the level needed for gamepad implementation) | Finished | Stuart Philpot | 5 | 5 | 5 (5 Hrs Worked) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | As a developer, I need to know how to use the api so that the code works correctly | Learn how to use johns pepper api | Finished | Stuart Philpot | 4 | 4 | 4 (4 Hrs Worked) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | As a developer, I need to create a prototype that can be tested so I can further develop the program | Combine this knowledge to create a protptype for gamepad control | Finished | Stuart Philpot | 10 | 10 | 10 | 10 (7 Hrs Worked) | 3 (3 Hrs Worked) | 0 | 0 | 0 | 0 | 0 | 0
|  | As a developer, I want to be sure that what I've developed works when put on Pepper | Test the prototype on pepper | Started | Stuart Philpot | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1:30(30 mins workd) | -2:45 (worked 4:15 hrs) | 0 | 0
| Tablet team - | Stuart Lancaster | Mykyta Kakaranza
| Website team - | Kate Leggott | Abigail Smith
| controller team - | Stuart Philpot
| Design cordinator | Calla Aitken